## Sheet1
SN | TASK NAME | TESTED AND APPROVAL | QA | Feat. Owner | Days |  | STATUS | From | To | Milestones | COMMENTS
1 | Setup And Structuring | Pending | Abhishek |  |  | Maximum Days | Pending | 02.14.2022 | 02.22.2022
| Database Structure |  |  | Akash | 1.5
| Code Setup |  |  | Parvesh And Akash | 2
| Cloud Setup |  |  | Parvesh And Akash | 3
| Admin Panel Structure (All Routings ready for designer) |  |  | Parvesh And Akash | 1
2 | Code Level Setup & Designing | Pending | Abhishek |  |  |  | Pending | 02.22.2022 | 03.11.2022
| Models & Services |  |  | Akash | 1
| Designs (Sign in, Forgot Password, Dashboard) |  |  | Vinod | 2
| APIs Login (Mobile App Sign Up STEP 1, Admin Login, Forgot Password) |  |  | Parvesh | 5 | 5
| Stripe Setup, Digisure SDK |  |  | Parvesh | 1 | 2
| AWS SDK Setup Notifications, Email Setup |  |  | Parvesh | 1
3 | SPRINT 1 | Pending | Abhishek |  |  |  | Pending | 03.14.2022 | 03.26.2022
| Functional Admin Panel Login, Forgot Password (Admin) |  |  | Parvesh And Akash | 5
| APIs (Mobile Sign up All 3 steps, vehicle listing / Admin, Employee Login & Manage employee section) |  |  | Parvesh And Akash | 5
| Admin Designs (Vehicles, Customers, Manage Employee) |  |  | Vinod | 17 | 13
| Testing the completed modules |  |  | Abhishek | 3
4 | SPRINT 2 | Pending | Abhishek |  |  |  | Pending | 03.27.2022 | 04.14.2022 |  | Mobile WORK would start THIS WEEK
| Admin Designs (Custom Settings, Revenue, Background Checks) |  |  |  | 5
| Mobile Design (Splash, Login, Signup, Vechile Listing) & Setup |  |  | Jitendra and Mohit | 21=14
| APIs (Digisure APIs, Argyle APIs) |  |  | Parvesh and Akash | 4
| Testing & Delivery Milestone 1 |  |  | Abhishek | 3
5 | SPRINT 3 | Pending | Abhishek |  |  |  | Pending | 04.15.2022 | 05.21.2022 |  | MILESTONE 1
| Mobile Design (Menus, Filters, Notifications, Book Now, Alerts) |  |  | Jitendra and Mohit | 17=11
| APIs (Add Vehicle, Listings for app, Vehicle Details) |  |  | Parvesh and Akash | 10
| Admin Functional (Vehicle Module) |  |  | Parvesh and Akash | 10
| Postman Documentation for Mobile Devs |  |  | Parvesh and Akash | 1
| Testing & Delivery Milestone 1 |  |  | Abhishek | 3
6 | SPRINT 4 | Pending | Abhishek |  |  |  | Pending | 05.21.2022 | 06.15.2022
| API( Admin Customer Module, Dashboard) |  |  | Parvesh and Akash | 7
Mobile Design (Vechile Details, Payment, Active Rentals, Profile, Extend Rentals, Remaining)
| APIs (Payment, Refunds, Transaction Fees) |  |  | Parvesh and Akash | 4
| Admin Functional (Customer Module, Dashboard) |  |  | Parvesh and Akash | 10
Testing Completed for Sprint 3
7 | SPRINT 5 | Pending | Abhishek |  |  |  | Pending | 06.16.2022 | 07.13.2022 |  | MILESTONE 2 UPTO SPRINT 3
Mobile Functional (Login/Register Module, Forgot Password)
| APIs (Start Rental, Promo Code) |  |  | Parvesh and Akash | 5
| Admin Functional (Rental Module Part 1 plus pre Inspection) |  |  | Parvesh and Akash | 11
| Postman Documentation for Mobile Devs |  |  | Parvesh and Akash
8 | SPRINT 6 | Pending | Abhishek |  |  |  | Pending | 07.14.2022 | 08.04.2022
Mobile Functional (Vechile List & Filters, Vechile Details)
| APIs (End Rental, Extend Rental) |  |  | Parvesh | 6
| Admin Functional (Rental Module Part 2 plus post Inspection) |  |  | Aksah | 11
Testing Completed upto Sprint 5
9 | SPRINT 7 | Pending | Abhishek |  |  |  | Pending | 08.05.2022 | 08.10.2022 |  | MILESTONE 3 UPTO SPRINT 4
Mobile Bugs Fixing Upto Sprint 6
| APIs (Notifications List and all working) |  |  | Parvesh | 4
| Admin Bug Fixing Upto Sprint 6 |  |  | Akash
10 | SPRINT 8 | Pending | Abhishek |  |  |  | Pending | 08.11.2022 | 08.22.2022
Mobile Functional (Promo Code, Payment API)
| APIs (Active Rental Listing, Cancel Rental & Fee refund) |  |  | Parvesh and Akash | 4
| Admin Functional (Inspection Module part 1) |  |  | Parvesh and Akash | 3
11 | SPRINT 9 | Pending | Abhishek |  |  |  | Pending | 08.23.2022 | 08.25.2022 |  | MILESTONE 4 UPTO SPRINT 7
Mobile Functional (Extend Rental, Payment Extend Rental)
| APIs (Payment method's, My Documents) |  |  | Parvesh and Akash | 3
| Admin Functional (Inspection Module part 1 - Pre Inspection) |  |  |  | Already covered with rentals
12 | SPRINT 10 | Pending | Abhishek |  |  |  | Pending
Mobile Bugs Fixing Upto Sprint 9
Admin Bug Fixing Upto Sprint 9
Test Report and improvements
13 | SPRINT 11 | Pending | Abhishek |  |  |  | Pending |  |  |  | MILESTONE 5 UPTO SPRINT 9
Mobile Functional (Cancel Rental, Payment Cancel Rental)
| Admin Functional (Inspection Module part 2 - Post Inspection) |  |  |  | 1
Mobile Build Ready Upto Sprint 9
14 | SPRINT 12 | Pending | Abhishek |  |  |  | Pending | 08.26.2022 | 09.01.2022
Mobile Functional (Completion of the app and fixes)
| Admin Functional (Vechile Switch, Background Checks) |  |  | Parvesh and Akash | 5
15 | SPRINT 13 | Pending | Abhishek |  |  |  | Pending |  |  |  | MILESTONE 6 UPTO SPRINT 11
Mobile Functional (Final fixes and updates)
| Admin Functional (Inspection Open and Completed Tasks, Manage User) |  |  |  | 4
16 | SPRINT 14 | Pending | Abhishek |  |  |  | Pending | 09.02.2022 | 09.07.2022
Support to Mobile devs for completion
Final Testing of mobile application
| Admin Functional (Custom Settings) |  |  | Parvesh and Akash | 4
17 | SPRINT 15 | Pending | Abhishek |  |  |  | Pending |  |  |  | MILESTONE 7 UPTO SPRINT 13
Fixes Mobile if any
Admin Functional Revenue
Client Testing and Updates
18 | SPRINT 16 | Pending | Abhishek |  |  |  | Pending
Final Delivery and release plan
Admin Interconnectivity of Pages
19 | SPRINT 17 | [9 empty] | MILESTONE 8 UPTO SPRINT 15
Bug Fixing
Admin Final Delivery
20 | RELEASE PHASE 1.1
Client Testing and Updates
Admin Final Delivery